## Gantt Chart
Task | Start | End | Jan-24 | Mar-24 | Jun-24 | Sep-24 | Dec-24 | Mar-25 | Jun-25 | Sep-25 | Dec-25 | Mar-26 | Jun-26 | Sep-26 | Dec-26
Ethics Approval | Jan 2024 | Sept 2024
Staff Training | Feb 2024 | Mar 2024
Recruitment Preparation | Feb 2024 | Mar 2024
Participant Recruitment | Jun 2024 | Dec 2024
Screening and Enrollment | Jun 2024 | Dec 2024
Baseline Data Collection | Apr 2024 | Jun 2024
Pregnancy Cohort Sub-Study | Apr 2024 | Dec 2025
Interim Analysis (Pregnancy) | Dec 2024 | Dec 2024
Final Analysis (Pregnancy) | Dec 2025 | Dec 2025
Intrapartum Sub-Study | Apr 2024 | Dec 2025
Postpartum Sub-Study | Jun 2024 | Dec 2026
Quarterly Reviews (Postpartum) | Sep 2024 | Dec 2026
Social Science Sub-Study | July 2024 | Dec 2026
Environmental Sub-Study | July 2024 | Dec 2026
Bi-weekly Uploads (Environmental) | July 2024 | Dec 2026
Monthly Analyses (Environmental) | July 2024 | Dec 2026
Initial Data Analysis | July 2025 | Jul 2024
Ongoing Analysis | Apr 2024 | Dec 2025
Interim Analyses (Ongoing) | Dec 2024 | Dec 2025
Final Data Analysis | Dec 2025 | Dec 2026
Interim Reports | Dec 2024 | Dec 2024
Drafting of Final Report | Apr 2026 | Jun 2026
Peer-Reviewed Publications | Jul 2026 | Dec 2026
Dissemination to Public | Jul 2026 | Dec 2026
Data Finalization | Jan 2026 | Dec 2027
Project Evaluation | Apr 2026 | Apr 2026
Study Close-Out | Jul 2026 | Jul 2026